## Release Stories
Project | Root Work Package | Version | Epic | Parent | Story ID | Subject | Goal | Acceptance Criteria | Non-Goals | Implementation Notes | Requirement IDs | Predecessors | Type | Status | Branch Name | OpenProject ID | Notes
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Foundation | Website V0.1 Portfolio Foundation | WS-001 | Establish portfolio application foundation | Create the React/FastAPI application foundation with environment-aware configuration, local PostgreSQL integration, and a testable frontend/API development workflow. | - React frontend and FastAPI backend run locally. - Frontend can call a health or equivalent backend endpoint. - Development configuration integrates with local wood-data-platform/PostgreSQL dependencies without production credentials. - Automated tests cover basic application startup or health behavior. - Development and production configuration paths are separated. | Does not implement portfolio content, contact capture, analytics instrumentation, production infrastructure, or deployment. | Use the existing repository conventions where available. Keep environment-specific settings outside application code and prepare the structure for Alembic-backed persistence. | FR-002, FR-004 |  | Story | New | feature/v0.1-ws-001-app-foundation | 380 | Foundation story for all later v0.1 work.
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Content | Website V0.1 Portfolio Foundation | WS-002 | Implement conceptual portfolio content framework | Implement the homepage, navigation, and reusable content system for the six conceptual portfolio sections, About, and Contact. | - Primary navigation exposes Data Generation, Data Collection, Data Modeling, Analytics, Machine Learning, Presentation, About, and Contact. - No standalone Projects section is present. - Markdown/Jinja2-backed content primitives support conceptual models, workflows, implementation examples, findings or tradeoffs, and repository/demo links. - The homepage communicates the end-to-end analytics lifecycle. - Repository links can be embedded as supporting reference implementations within conceptual content. | Does not require every conceptual section to have equal content depth or implement contact persistence, RudderStack, analytics transformations, or production deployment. | Treat conceptual sections as the primary taxonomy. Keep project and repository references subordinate to the concept being explained. | FR-001, FR-003, FR-014, FR-016 | WS-001 | Story | New | feature/v0.1-ws-002-content-framework | 381
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Lead Capture | Website V0.1 Portfolio Foundation | WS-003 | Implement contact lead capture | Provide an optional contact form that validates and persists inbound submissions as operational application data. | - Contact form is accessible from the site. - FastAPI validates accepted submissions and returns explicit success and error responses. - Contact submissions are persisted in PostgreSQL through a version-controlled Alembic migration. - Contact data is stored separately from analytics event data. - Failed validation or persistence does not create a false success state. | Does not add CRM integration, email automation, qualification scoring, or a consulting-services sales funnel. | Model contact submissions as operational data. Keep the form optional and visually secondary to portfolio content. | FR-015, QR-006 | WS-002 | Story | New | feature/v0.1-ws-003-contact-capture | 382
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Instrumentation | Website V0.1 Portfolio Foundation | WS-004 | Implement application event instrumentation | Define the application-owned event contract and instrument meaningful portfolio interactions through the RudderStack client SDK. | - Stable application-owned event names and properties are documented in code or configuration. - Page views, navigation or CTA interactions, conceptual-section engagement, outbound repository/demo interactions, and contact conversion are instrumented. - Instrumentation uses the RudderStack client SDK consistently. - Contact form payload data is not duplicated into analytics events beyond the minimum conversion signal. - Event payloads are shaped for downstream dbt transformation. | Does not implement downstream dbt models, dashboards, attribution models, or third-party analytics products beyond RudderStack. | Keep event definitions centralized and application-owned so collection technology can change without redefining product semantics. | FR-008, FR-011 | WS-002, WS-003 | Story | New | feature/v0.1-ws-004-event-instrumentation | 383
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Analytics Pipeline | Website V0.1 Portfolio Foundation | WS-005 | Establish production analytics pipeline | Route raw production events to cloud PostgreSQL and establish the initial dbt/Dagster transformation path from the Beelink without making analytics compute a public-runtime dependency. | - RudderStack delivers production events to a raw analytics area in cloud PostgreSQL. - Operational application data, raw events, and transformed analytics models have explicit schema or role boundaries. - A least-privilege analytics role can read required raw data and perform approved transformations. - Initial dbt models can transform production event data successfully. - Dagster can orchestrate the dbt workload over a secured connection from the Beelink. - Public site and event ingestion continue when Dagster/dbt or the Beelink are unavailable. | Does not require near-real-time transformation, high availability for the Beelink, advanced reporting automation, or separate production databases for every data domain. | Use one production PostgreSQL service initially with clear schema and role separation unless infrastructure constraints justify otherwise. | FR-009, FR-010, FR-012, QR-004, QR-005 | WS-004, WS-006 | Story | New | feature/v0.1-ws-005-analytics-pipeline | 384
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Infrastructure | Website V0.1 Portfolio Foundation | WS-006 | Provision production infrastructure | Provision DigitalOcean application and PostgreSQL infrastructure with environment separation, protected secrets, backups, and no synchronous dependency on the home network. | - Production application hosting is available in DigitalOcean. - Production PostgreSQL is available in DigitalOcean and is logically separated from development. - Production secrets and database credentials are injected outside source control. - Public application, API, contact capture, and event-ingestion paths do not require the Beelink or home network. - Database/network access is restricted to required services and roles. - Backup and recovery configuration is established for the production PostgreSQL deployment. | Does not require multi-region deployment, Kubernetes, active-active failover, or separate managed databases for application and analytics workloads. | Prefer DigitalOcean Managed PostgreSQL when budget permits; a same-Droplet PostgreSQL deployment is acceptable only with persistent storage, backups, restricted access, and a migration path. | FR-005, FR-007, FR-013, QR-001, QR-002, QR-003 | WS-001 | Story | New | feature/v0.1-ws-006-production-infrastructure | 385
Website | Website V0.1 Portfolio Foundation | V0.1 Portfolio Foundation | Delivery | Website V0.1 Portfolio Foundation | WS-007 | Implement CI/CD and production release | Automate build, test, migration, secret injection, and production deployment so the v0.1 portfolio can be released repeatably. | - CI builds and tests the frontend and backend. - Deployment injects environment-specific production configuration from the secret store. - Alembic migrations are applied automatically as part of the production deployment process. - Deployment targets the DigitalOcean production application environment. - A production smoke test verifies the public site, API, contact flow, and event-ingestion path after deployment. - A failed build, test, migration, or deployment step fails the release workflow rather than reporting success. | Does not implement blue/green deployment, canary release management, multi-environment promotion workflows, or advanced release observability. | Keep migration execution version-controlled and deployment-driven. Production release must not require manual database credential changes in source code. | FR-006, QR-002, QR-006 | WS-003, WS-005, WS-006 | Story | New | feature/v0.1-ws-007-cicd-production-release | 386 | Final release story.

## Release Metadata
Field | Value
Artifact Type | Release-specific implementation plan
Project | Website
Release | V0.1 Portfolio Foundation
OpenProject Version | V0.1 Portfolio Foundation
Release Plan | TBD — implementation scope approved from Website Requirements
Requirements Source | Website Requirements
Root Work Package | Website V0.1 Portfolio Foundation
Release Outcome | Deploy a production portfolio website organized around the analytics lifecycle, with reusable conceptual content, repository-backed reference implementations, contact capture, first-party event instrumentation, and a functioning cloud-to-dbt analytics path.
Release Requirement IDs | FR-001–FR-016; QR-001–QR-006
Known Limitations | V0.1 establishes the six conceptual routes and production architecture; content depth may be uneven across sections. No standalone Projects section is included.
Planning Status | Draft
Story Count | 7

## Instructions
Rule | Guidance
Workbook Scope | One workbook represents exactly one software release / OpenProject Version. Do not place stories for another release in this workbook.
Version Consistency | Every Release Stories row must use the exact OpenProject Version defined in Release Metadata.
Traceability | Every story must reference approved requirement IDs assigned to this release; every release requirement must be covered by at least one story or explicitly deferred.
Dependencies | Use only genuine prerequisites. No story may depend on work assigned to a later release; prior-release prerequisites must already be completed.
Future Work | Do not add unscheduled ideas, later-release capabilities, or speculative stories to this workbook.
Artifact Location | Store each release implementation workbook in Projects/{{PROJECT_NAME}}/Releases/{{OPENPROJECT_VERSION}}/ and name it {{PROJECT_NAME}} {{OPENPROJECT_VERSION}} Implementation.xlsx.
Completion | When the release closes, use completed stories for release notes/changelog and archive the release implementation artifact.